## Correspondence Register
CORRESPONDENCE REGISTER — PERIOD 11
Incoming, with date of receipt
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Ref | From | Dated | Received | Subject
PDC-LTR-PMC-024 | Engineer | 2027-01-06 | 2027-01-06 | Monthly progress — comments
PDC-LTR-PMC-025 | Engineer | 2027-01-14 | 2027-01-15 | Determination — PDC-CLM-001 and EI-007 (Sub-Cl. 3.7)
ILM-LTR-014 | Ilmatek TP-005 | 2027-01-19 | 2027-01-19 | EI-007 — SF-2291 supplier quotation enclosed

## IPC-09 Extract
INTERIM PAYMENT CERTIFICATE NO. 9 — EXTRACT
Certified 30.11.2026 · temporary works section
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Item | Description | Certified (EUR)
TW.01 | Site accommodation — extension of hire | 14200
TW.04 | Temporary works — power (extension of temporary supply) | 6800
TW.06 | Temporary lighting — winter provision | 9350
Note: TW.04 covers the extension of the temporary supply to 31.03.2027, invoice INV-SBI-2216.

## TIA Extract — PDC-CLM-001
TIME IMPACT ANALYSIS — FLOAT POSITION
Annexed to PDC-CLM-001 as submitted · working days
SYNTHETIC DEMONSTRATION DATA — NOT A REAL PROJECT
Activity | Description | Total float (baseline) | Total float (scenario) | Critical
ST-1300 | L4 structural handover (TP-001 Kallio) | 55 | 85 | No
ST-1310 | L4 fit-out commencement | 0 | 0 | Yes
EN-110 | 110 kV energisation (Employer) | 0 | 0 | Yes
ST-1400 | Commissioning and handover | 0 | 0 | Yes
Note: ST-1300 carries substantial float in both baseline and scenario. The 9 wd L4 slip is absorbed within it and does not reach the Time for Completion.
Note: this sheet is an extract of Annex TIA to PDC-CLM-001, submitted 30.11.2026 and not returned as deficient.