# Tender brief — Säterinpuistontie välillä Leppävaarankatu – Turuntie

Prepared: 7 October 2026 · Prepared for: managing director, Kymenlaakso groundworks & municipal-engineering subcontractor Discipline: public procurement watch — Hilma, Finland Reading note: this brief is built from the public contract notice only. The buyer's procurement documents (tarjouspyyntö, bill of quantities, contract terms) sit behind a supplier-portal registration and were not retrieved in this run. Anything not in the notice is written "not stated". Every interpretive assumption is marked ASSUMPTION and must be re-based on the procurement documents before any bid work starts.

---

# 1. Notice identification

Note on the record: a lookup of the notice by its bare numeric id returns two index hits; filtering by the notice number returns exactly one record, and the notice page shows no linked notices. Conclusion: there is no corrigendum and no duplicate notice for this procurement. (Assessed 7.10.2026.)

---

| Item | Value | Source |
| --- | --- | --- |
| Notice type | KANSALLINEN HANKINTAILMOITUS — national contract notice (FI/TED eForms E3) | Hilma notice page, notice header |
| Notice number | 2026-057797 | Hilma |
| Hilma internal id | EF-57797 (procedureId 37638) | Hilma record |
| Competition ID (kilpailutustunniste) | QQ/26/037638/000 | Hilma, "Osa" tab |
| Buyer's diary no. | 3783/02.08.00/2026 | Cloudia/Espoo portal page |
| Contract folder id | e33c2f42-9e4a-429b-886d-d6ce9ca0e308 | Hilma record |
| eForms id | 49f2357e-48d8-4c02-aab9-12c8e13e419a-01 | Hilma record |
| Published | 23.9.2026 15:39 (UTC+03:00) | Hilma notice page |
| Corrigendum / linked notices | None. "Liittyvät ilmoitukset: Ei liittyviä ilmoituksia"; isCorrigendum = false; isCancelled = false | Hilma notice page + record |
| Notice link | https://www.hankintailmoitukset.fi/fi/public/procedure/37638/enotice/57797 | — |

# 2. Buyer

Geographic reality check: the buyer is in the Helsinki metropolitan area, roughly 150 km from the firm's Kymenlaakso base — outside its home region (FI1C4/FI1C7). This is the single largest commercial penalty of this opportunity and is carried into the recommendation below.

The buyer's contact was not used. No contact was made and nothing was submitted, per instruction.

---

| Item | Value |
| --- | --- |
| Contracting authority | Espoon kaupunki (City of Espoo) |
| Tendering unit | Espoon kaupungin hankintapalvelut |
| Business ID | 0101263-6 |
| Address | PL 640, 02070 Espoon kaupunki, Finland |
| NUTS region | FI1B1 Helsinki-Uusimaa |
| Contact point (BT-502/503/506) | Pasi Myllys · pasi.myllys@espoo.fi · +358 438253213 |

# 3. Scope

The notice describes the works as (verbatim, Finnish):

Reading it out:

CPV: 45200000 (works for complete or part construction and civil engineering work) · Lots: a single lot, LOT-0000. The notice carries no quantity list and no bill of quantities — the BoQ is in the procurement documents.

---

"Säterinpuistontie välillä Leppävaarankatu – Turuntie on uusi alueellinen kokoojakatu, jolla parannetaan liikenteen toimivuutta ja turvallisuutta Leppävaaran alueella. Katu muodostaa uuden auto-, pyörä- ja jalankulkuliikenteen yhteyden Turuntien ja Leppävaarankadun välille. Katu alittaa Helsinki-Turku rautatien ja radan pohjoispuolelle suunnitteilla olevan Rantaradanbaanan. Työ käsittää, katujen ja vesihuollon rakennustöitä. Töitä tehdään rautatie- ja katualueilla osin yleisen liikenteen parissa sekä puistoalueilla. Urakassa käytetään Infrakit-projektipankkia, tietomalleja ja koneohjausta. Huomiota kiinnitetään myös urakassa käytettävien luonnonkiveysmateriaalien päästöarvoihin."

- A new regional collector street between Leppävaarankatu and Turuntie in Leppävaara, improving traffic flow and safety — a new connection for vehicles, cyclists and pedestrians.

- The street passes under the Helsinki–Turku railway and under a future line (Rantaradanbaana) planned north of the railway. It is built in a railway area.

- The work comprises street construction and water-services (water & sewer) construction works — the firm's declared trade on both halves.

- Works take place in railway and street areas, partly among live public traffic, and in park areas.

- The contract uses the Infrakit project bank, information models and machine control.

- Attention is paid to the emission values of natural-stone paving materials used in the contract.

# 4. Contract form and legal regime

ASSUMPTION (contract form): for a Finnish municipal street-and-water contract of this kind the conventional form is a kokonaisurakka (single lump-sum contract for the whole work) under the YSE 1998 general conditions for building contracts, with technical execution following the municipal infrastructure norms (InfraRYL / MaaRYL). The Infrakit project bank is the buyer's chosen data environment. This is an assumption, not a notice fact — confirm in the tarjouspyyntö. Note for the file: the working language of the project is Finnish; all bid documents are in Finnish (see §5).

---

| Item | Value |
| --- | --- |
| Legal basis | Laki julkisista hankinnoista ja käyttöoikeussopimuksista (hankintalaki) 1397/2016 — national Finnish procurement act |
| Notice regime | National procedure; not published EU-wide (isNationalProcurement = true, isEuProcurement = false) |
| Estimated value vs national threshold | The notice confirms the estimated value is at least the national threshold ("vähintään kansallisen kynnysarvon suuruinen: Kyllä") |
| Procedure | Avoin menettely (open procedure) |
| Framework agreement | No (includesFrameworkAgreement = false) · Dynamic purchasing system: no |
| Contract form (urakkamuoto) | not stated in the notice |
| General conditions | not stated in the notice |
| Contract duration / commencement | not stated in the notice |
| Options / renewals | not stated in the notice |
| Review authority | Markkinaoikeus (Market Court), Radanrakentajantie 5, 00520 Helsinki · markkinaoikeus@oikeus.fi · +358 295643300 |

# 5. Procedure and time limits

Calendar consequence: from today (7.10.2026) there are 19 days to the tender deadline and 12 days to the question deadline. Any question the firm wants to ask must be in by 19.10.2026 12:00 or it will not be answered. The 2-month tender validity means a price submitted on 26.10.2026 is held open until roughly late December 2026.

---

| Milestone | Date / value | Source |
| --- | --- | --- |
| Notice published | 23.9.2026 | Hilma |
| Deadline for questions (lisätietojen määräaika) | 19.10.2026 12:00 (UTC+03:00) | Hilma "Määräajat" tab, TED BT-13 |
| Deadline for tenders | 26.10.2026 12:00 (UTC+02:00) | Hilma "Määräajat" tab, TED BT-131 |
| Tender validity | 2 months from the submission deadline | Hilma "Määräajat" tab, TED BT-98 |
| Site visit / information session | not stated — no site visit or info session appears in the notice | Hilma record (no siteVisit / infoSession field) |
| Submission channel | Electronic submission is mandatory (BT-17 = "Pakollinen") via the Cloudia/Tarjouspalvelu supplier portal (BT-18) | Hilma "Osallistuminen" tab |
| Bid language | suomi — Finnish only (BT-97) | Hilma "Osallistuminen" tab |

# 6. Contract value

---

- Not stated in the notice. The notice's estimated-value field and currency field are both empty, and the lot carries no value either. The notice states only that the value is at least the Finnish national threshold (§4).

- External context, deliberately excluded from this brief: earlier drafts carried a public-web street-plan figure for this scheme (around 13 M€) and a wider rail-project figure. Both have been REMOVED on review, because the notice itself carries no value and an unverified figure can anchor the reader. The position is simply: value not stated in the notice. If the firm wants the market context, it should be obtained commercially — it plays no part in this brief's recommendation.

- Participation model — ONE model, stated: the firm bids as a NAMED SUBCONTRACTOR to the main contractor for the groundworks package (street structure, water and sewer networks, cable trenches, foundations). A prime bid is a stated fallback only, to be considered if the procurement documents show the contract is sub-scale. This follows from notice facts alone, not from any external figure: the scope names a railway underpass beneath the Helsinki-Turku railway and a planned second line, works partly among live public traffic, and an Infrakit and machine-control data environment — a civil package that in practice sits under a main contractor, and the firm's declared client base includes main contractors. The notice does not state the contract value; quantify only after the documents are read.

# 7. Award criteria

---

- not stated in the notice. The notice record carries no award criteria, no selection criteria and no suitability requirements; the "Päätöksenteon perusteet" and "Soveltuvuusvaatimukset" sections on the Hilma page are populated from the buyer's documents, which are not public without portal registration.

- The notice does state where the exclusion criteria live: "Poissulkemisperusteet ilmoitetaan hankinta-asiakirjoissa" — the exclusion grounds are given in the procurement documents (TED BT-806).

- ASSUMPTION (award model): for national Finnish works contracts of this type the comparison is commonly either lowest price or lowest price with a quality component (a quality/price weighting, often 30/70 or 40/60; occasionally a scored quality section covering delivery schedule, resources and environmental measures). This is an assumption and must be confirmed — it determines whether this is a price race or a quality competition.

# 8. Suitability and eligibility requirements

---

- not stated in the notice. The notice carries no turnover requirement, no reference requirement, no key-personnel requirement, no plant requirement and no ESPD structure.

- In a national procedure the buyer satisfies itself of bidder reliability and suitability from the procurement documents and its own suitability/supplier questionnaire. (Corrected 7.10.2026: an earlier draft referred to the ESPD — the ESPD is an EU single-market instrument and is not used in a purely national Finnish procedure below the EU threshold. The form the buyer actually requires is not stated in the notice.)

- ASSUMPTION (expected minimum evidence — standard Finnish practice): trade-register extract; tax and employer-contribution certificates (verotodistus / työnantajarekisteriote); pension-insurance and accident-insurance certificates; a statement of the firm's turnover and financial ratios; references for comparable street/water works; and possibly named key personnel and a plant list. Confirm in the tendering documents.

# 9. Sustainability and strategic obligations the buyer has flagged

The notice's strategic-procurement flags are set to true for: energy efficiency, low carbon, circular economy, compliance with working conditions (justWorkingConditions) and SME participation considered. Set to false: biodiversity, employment condition, code of conduct, innovation.

Practical reading for the bid: expect requirements on emission values for natural-stone materials (explicitly named in the scope description), low-carbon and circular-economy handling of materials (reuse/recycling, low-emission haulage, mass balance), and contractual compliance with collective agreements and working conditions — the last of these is a mandatory obligation and a common ground for exclusion if breached.

---

# 10. Risks and ambiguities

---

| # | Risk / ambiguity | Why it matters | Status |
| --- | --- | --- | --- |
| R1 | Procurement documents require registration. The notice states document access is not restricted (BT-14 = "Ei"), but the buyer's Cloudia/Tarjouspalvelu portal in practice refuses to display the documents without registering and logging in. They were not retrieved in this run. | The whole basis of a price — quantities, award criteria, contract terms — is unknown. Registering on the portal is the first action. | Open — action needed |
| R2 | Award criteria not in the notice. Unknown whether this is lowest price or a price/quality weighting. | Determines bidding strategy: a price race for a small firm against larger contractors is materially different from a quality competition. | Open |
| R3 | Value and scale unknown from the notice, but the surrounding scheme is ~13 M€. | A contract of that scale is beyond a small firm as prime; the realistic position is subcontractor. Affects mobilisation cost and risk exposure. | Open — provisional |
| R4 | 2-month tender validity. | The price is held firm into late December 2026; plant, labour and material rates must carry that. | Open |
| R5 | Railway interface. The street underpasses the Helsinki–Turku railway and a planned second line; works in a railway area, partly among live traffic. | Safety-critical interfaces, possible rail-authority approvals and possession arrangements; drives cost and risk. | Open — likely significant |
| R6 | Infrakit, information models and machine control required. | A genuine capability and cost gap if the firm does not already run machine-control plant and Infrakit workflows; also a data-management workload. | Open |
| R7 | Natural-stone material emission values named as a focus. | Probably a documented, verifiable requirement — sourcing and evidence needed. | Open |
| R8 | Finnish-language bid, mandatory electronic submission, national procedure. | Administrative, but a hard gate: bid in Finnish through the portal only. | Known |
| R9 | No site visit in the notice. | No scheduled opportunity to inspect; site conditions (railway, live traffic, park areas) carry estimate risk. | Open |
| ~~R10~~ | ~~Possible corrigendum~~ | Resolved: no linked notices; no corrigendum. Removed. | Closed |
| R11 | Bidding cost before the documents are read. | Preparing a bid of this scale in 19 days, blind to quantities and criteria, is expensive relative to win probability. | Open — commercial |

# 11. Questions to put to the buyer (all before 19.10.2026 12:00)

1. Please confirm the procurement documents are available without registration, or advise the correct access route — the notice states access is unrestricted (BT-14) but the portal asks for a log-in. 2. Award criteria and their weightings, and whether there is a quality component. 3. The estimated total value of the contract and the bill of quantities (or a quantity list by structure type). 4. Contract form and general conditions — is this a kokonaisurakka under YSE 1998? Which technical norms (InfraRYL/MaaRYL) apply? 5. Payment terms and schedule, retention, and the basis of payment (lump sum / measurement). 6. Securities: performance bond percentage, warranty period, warranty-period security, and any parent-company or other security requirement. 7. Contract duration and intended commencement. 8. Infrakit, information-model and machine-control requirements — which tolerance classes, who provides and maintains the data environment, and whether machine-control files are supplied. 9. The natural-stone emission-value requirement — which standard, which limits, and how compliance is demonstrated. 10. Railway-area works — are the underpass and railway-area works inside this contract, or in a separate contract with the rail authority / main contractor? Which approvals and possessions are in the contractor's scope? 11. Whether partial delivery or use of a named subcontractor is permitted, and whether a consortium or subcontractor arrangement may be used to meet the requirements. 12. Whether a site visit or site access can be arranged.

---

# 12. Recommendation

BID — conditional, with a subcontractor route preferred. Do not spend estimating effort before R1 is closed.

The honest position: this is the best scope match found in the window — the notice's own words ("katujen ja vesihuollon rakennustöitä") are the firm's declared trade on both halves — but it is 150 km from base, the surrounding scheme is ~13 M€-scale, and the criteria, quantities and contract terms are all still behind a registration wall. On the evidence available, the defensible course is:

1. First action — register on the buyer's portal and download the procurement documents (free, ~15 minutes). Nothing below can be firm until this is done. This is the gating step. 2. Then, within 12 days, ask the §11 questions — particularly award criteria, value/quantities, contract form and the railway-interface split — before the 19.10.2026 question deadline. 3. Decide finally on the downloaded documents, against a plain test: if it is a lump-sum kokonaisurakka of ~13 M€ scale, decline to prime it and instead approach the likely main contractors about the groundworks/pipework subcontract package — that is a realistic, profitable and low-risk position for a firm of this size. 4. If the contract proves to be a smaller phase (a street section, or a package within the programme) with a value in the firm's band, then bid as prime, with the Infrakit/machine-control capability gap (R6) resolved first.

Runner-up and the alternative: the weighted screening metric put the Lahden Niemi harbour contaminated-soil remediation marginally ahead of Espoo (3.24 against 3.02), but it is contaminated-soil work rather than the declared street/water trade and closes in only 9 days, so it is not a clean substitute. The genuinely strongest regional action this fortnight is not a bid at all: engaging Kymenlaakson Sähköverkko Oy's market dialogue for distribution-network construction and maintenance 2028–2030 (join by 20.10.2026) — in-trade (cable trench and network construction), in-region, and free. See the screening record.

Basis and status of any figures: no price or pricing basis is proposed in this brief. If a pricing basis is used later it must be stated as one single basis, and any figure derived before the bill of quantities is read must be labelled PROVISIONAL / ranking-only.

Note on the selection metric (added 7.10.2026): the weighted screening scores are a screening aid, not the decision. On the metric Lahti leads (3.24) and Espoo is second (3.02); Espoo is selected because the firm's rule is fit first, and Espoo is the only notice matching the declared trade on both halves (trade-fit 5 against Lahti's 3), with the better deadline as tie-breaker. If the firm's operating radius is the binding constraint, the metric's preference for the closer Lahti job is the honest counter-argument, and it must be decided before Lahti closes on 16.10.2026.