## Sheet 1
# | Source ref | Document / form the bid must contain | Who provides it | Status | Deadline | Source anchor | Note
1 | Notice §5 / BT-14, BT-18 | Supplier-portal registration (Cloudia / Tarjouspalvelu, Espoo) | We — office | not started | by 19.10.2026 | Hilma "Osallistuminen" tab, notice 2026-057797: notice says access not restricted (BT-14 = "Ei") but the portal requires register and log in | GATING ACTION — no other row can close until this is done
2 | BT-806 | Full procurement-documents package (tarjouspyyntö + attachments, incl. the bill of quantities) | We — download from portal | not started | by 19.10.2026 | TED BT-806: "Poissulkemisperusteet ilmoitetaan hankinta-asiakirjoissa" | Source of award criteria, suitability requirements, contract terms and quantities — all currently "not stated"
3 | BT-131, BT-97 | The tender offer itself | We — office | not started | 26.10.2026 12:00 | Hilma "Määräajat" tab, TED BT-131 | Bid language Finnish only (BT-97)
4 | BT-17, BT-18 | Electronic submission through the buyer's portal | We — office | not started | 26.10.2026 12:00 | Hilma "Osallistuminen" tab, BT-17 = "Pakollinen" | No paper or e-mail route is offered
5 | Notice §8 — not stated | Buyer's suitability / supplier questionnaire (the form the buyer actually requires) | We — office | missing | when documents are read | notice 2026-057797 carries no suitability requirements; the required form is to be confirmed in the tarjouspyyntö | CORRECTED 7.10.2026: an earlier draft assumed an ESPD. The ESPD is an EU single-market instrument and is not used in a purely national Finnish procedure
6 | ASSUMPTION — standard FI practice | Trade-register extract (kaupparekisteriote) | We / accountant | missing | before submission | Not in the notice — assumed standard national-procedure evidence | Confirm the exact list in the tarjouspyyntö
7 | ASSUMPTION — standard FI practice | Tax certificate (verotodistus) | Accountant | missing | before submission | As row 6 | —
8 | ASSUMPTION — standard FI practice | Employer-register extract and pension-insurance certificate | Accountant | missing | before submission | As row 6 | —
9 | ASSUMPTION — standard FI practice | Accident-insurance certificate | Insurer | missing | before submission | As row 6 | —
10 | ASSUMPTION — standard FI practice | Liability-insurance certificate | Insurer | missing | before submission | As row 6 | —
11 | ASSUMPTION — standard FI practice | Financial statements, turnover declaration and financial ratios | Accountant | missing | before submission | As row 6 | No financial data of any kind exists in the project
12 | ASSUMPTION — standard FI practice | Reference list — comparable street and water-services works | We — office | missing | before submission | As row 6 | The firm's references will be as a named subcontractor, not as prime — legitimate, and to be stated plainly
13 | ASSUMPTION — standard FI practice | Key-personnel CVs / competence summaries | We — office | missing | before submission | As row 6 | —
14 | ASSUMPTION — standard FI practice | Personnel competence certificates (occupational safety card, pipework, hot work, first aid) | HR / training | missing | before submission | As row 6 | —
15 | Notice §3 scope | Plant and equipment list, incl. machine-control capability | We — plant | missing | before submission | Notice 2026-057797 scope: "Urakassa käytetään Infrakit-projektipankkia, tietomalleja ja koneohjausta" | Machine control is named as a contract requirement — no plant register exists in the project
16 | Notice §3 scope | Infrakit / machine-control competence statement and data-environment plan | We — site | missing | before submission | As row 15 | —
17 | Notice §3 scope | Natural-stone material emission-value documentation | Procurement / suppliers | missing | before submission | Notice §3: "Huomiota kiinnitetään myös urakassa käytettävien luonnonkivimateriaalien päästöarvoihin" | Which standard, which limits and how compliance is shown are not stated — buyer question 9
18 | ASSUMPTION — standard FI practice | Technical / quality plan | We — site | not started | before submission | As row 6 | —
19 | ASSUMPTION — standard FI practice | Programme / schedule | We — site | not started | before submission | As row 6 | Contract period and commencement are not stated in the notice — no time-based programme can be built yet
20 | HSE regime FI | HSE plan and site safety arrangements | We — HSE | missing | before submission | FI regime: työturvallisuuslaki 738/2002 + Vna 205/2009, TR-mittaus weekly index | —
21 | HSE regime FI | Occupational-safety statistics (TR-mittaus history, accident frequency) | We — HSE | missing | before submission | As row 20 | No HSE data exists in the project
22 | Notice strategic flags | Working-hours and working-conditions reporting commitment | HR | missing | before submission | Notice flags: justWorkingConditions = true | Mandatory obligation; a breach is a ground for exclusion
23 | ASSUMPTION — standard FI practice | Subcontractor and supplier list with reliability evidence | Procurement | missing | before submission | As row 6 | —
24 | Notice §3 scope | Temporary traffic-management plan | We — site | not started | before submission | Notice §3: "Töitä tehdään rautatie- ja katualueilla osin yleisen liikenteen parissa" | —
25 | Notice §3 scope | Railway-area interface plan and any rail-authority approvals | We + rail authority | not started | before submission | Notice §3: "Katu alittaa Helsinki-Turku rautatien" | Whether the underpass sits inside this contract is not stated — buyer question 10
26 | Notice strategic flags | Environmental / circular-economy plan | We — site | not started | before submission | Notice flags: lowCarbon = true, circularEconomy = true | —
27 | ASSUMPTION — standard FI practice | Site-management and works-security statement | We — site | not started | before submission | As row 6 | —
28 | Notice §6 — securities not stated | Bid security / tender guarantee | Bank or insurer, if required | missing | confirm before submission | Notice 2026-057797 is silent on securities; no tender security is stated anywhere in it | CORRECTED 7.10.2026: previously marked "not required". The notice is silent, not negative, so the honest status is "missing" pending the tarjouspyyntö
29 | ASSUMPTION — FI practice | Performance bond / contractor's security | Bank or insurer | missing | contract stage | Not in the notice — Finnish practice commonly ~10% of contract value | Practice figure, NOT a notice fact — confirm in the tarjouspyyntö
30 | ASSUMPTION — FI practice | Warranty-period security | Bank or insurer | missing | contract stage | Not in the notice — Finnish practice commonly ~2–5% | Practice figure, NOT a notice fact
31 | ASSUMPTION — standard FI practice | Certificate of compliance with the applicable collective agreement | HR | missing | before submission | As row 6 | —
32 | BT-131 | Signed tender letter and completed price schedule | We — office | not started | 26.10.2026 12:00 | TED BT-131 — the offer itself | Price-schedule structure is unknown until the documents are read. No figure may be finalised before the bill of quantities is read — anything earlier is PROVISIONAL / ranking-only
33 | ASSUMPTION — standard FI practice | Material conformity certificates and approvals (CE / InfraRYL) | Suppliers | missing | before submission | As row 6 | —

## Status summary
Status | Count
not started | 11
in progress | 0
ready | 0
missing | 22
not required | 0
Total rows | 33