## 1 Sources
Sources & assumptions — every input fact and its origin (user's pour brief; working directory empty, no project files; no minutes exist because the sources contain none)
Ref | Item | Value | Source | Type | Note
S01 | P1 raft bay A volume | 24 m³ | User message (pour list) | Substantive | 3 loads × 8 m³
S02 | P1 pump window | 07:00–09:20 | User message | Substantive | 140 min
S03 | P1 drive Tikkurila→site | 25 min | User message | Substantive | One-way, no traffic allowance
S04 | P2 core wall volume | 16 m³ | User message | Substantive | 2 loads × 8 m³
S05 | P2 pump window | 07:30–09:30 | User message | Substantive | 120 min
S06 | P2 drive | 35 min | User message | Substantive | One-way
S07 | P3 column heads volume | 8 m³ | User message | Substantive | 1 load × 8 m³
S08 | P3 pump window | 08:30–10:20 | User message | Substantive | 110 min
S09 | P3 drive | 20 min | User message | Substantive | One-way
S10 | Truck capacity | 8 m³ | User message | Substantive | One full load per trip
S11 | Trucks booked | 6 (T1–T6) | User message | Substantive | Current plan: one load each
S12 | Loading time at plant | 10 min | User message | Substantive | Batch→depart
S13 | Freshness rule | placed ≤ 90 min from batching | User message (spec) | Substantive | Runs from T0=batch start, not depart
S14 | Continuity rule | ≤ 25 min between loads, same pour | User message | Substantive | Measured discharge-end → next discharge-start
S15 | Plant name | Tikkurila | User message | Non-substantive | Label only
S16 | Pour names | Raft bay A / Core wall / Column heads | User message | Non-substantive | Labels only
S17 | Pour date | Thursday | User message | Non-substantive | No calendar date given
AS-01 | Return-leg drive = outbound | 25/35/20 min | ASSUMPTION | Assumption | No traffic allowance; sensitivity V2/V7 tested
AS-02 | Discharge 10 min per 8 m³ load | ≈48 m³/h pump | ASSUMPTION | Assumption | Sensitivity V1 (15 min), V8 (20 min) tested
AS-03 | Plant loads one truck at a time | single bay | ASSUMPTION | Assumption | Schedule keeps 10-min slots exclusive
AS-04 | Truck may wait loaded on site | allowed | ASSUMPTION | Assumption | 90-min rule still enforced (P3-L1 waits 25 min for the PUMP — see AS-09)
AS-05 | Plant batching available from 06:00 | earliest T0 06:00 | ASSUMPTION | Assumption | Plan's earliest batch 06:05; V5 (06:30) tested
AS-06 | Batch times on 5-min grid | plant practice | ASSUMPTION | Assumption | All T0 in plan are :00/:05/:10…
AS-07 | Pump serves one truck at a time | no parallel discharge | ASSUMPTION | Assumption | Loads on a pour sequenced, no overlap
AS-08 | Minimum turnaround buffer between a truck's loads | 5 min | ASSUMPTION | Assumption | Adopted as hard floor in the solve; achieved buffers are 25 min
N01 | Slump / retarder limits | not modelled | NOT PROVIDED | Open item | Confirm with spec before issuing — see escalation card O4
N02 | Pump priming / setup time | not modelled | NOT PROVIDED | Open item | If >0, first discharge starts later — see escalation card O5
N03 | Washout / stand-by between pours | not modelled | NOT PROVIDED | Open item | No effect on truck count — see card O6
AS-09 | Single pump shared across pours; relocation between pour areas | 10 min | ASSUMPTION | Assumption | P2→P3 transition uses exactly 10 min (P2-L2 ends 09:05 → P3-L1 starts 09:15); P1→P2 has 75 min. If relocation >10 min, P3-L1 slips within its window (close-margin 55) capped by freshness margin 25

## 2 Model
Constraint model & arithmetic — the rules, as modelled, and their verification
Ref | Rule / computation | Statement as modelled | Check
C1 | Volume → loads | P1 24 m³ ÷ 8 = 3 loads; P2 16 ÷ 8 = 2; P3 8 ÷ 8 = 1; total 48 m³ = 6 loads | 6 = 3+2+1 ✓
C2 | Loading | depart = T0 + 10 min | all rows ✓
C3 | Drive | arrive = depart + drive (P1 25 / P2 35 / P3 20) | all rows ✓
C4 | Pump window | discharge start ≥ window open AND discharge end ≤ window close | all rows ✓
C5 | Freshness | discharge end ≤ T0 + 90 (from batching, not depart) | min margin 25 min ✓
C6 | Continuity | next discharge start − prev discharge end ≤ 25 (same pour); no pump overlap | margins 25/25/25 ✓
C7 | Truck turnaround | next T0 ≥ prev discharge end + return drive (+5 min buffer adopted) | buffers 25 min ✓
C8 | Plant single bay | loading slots (10 min) do not overlap | 06:05/06:25/06:35/08:00/08:10/08:20 ✓
LB | Lower bound (proof) | If one truck served two P1 loads: return 25 + load 10 + drive 25 forces the second discharge to start ≥ 60 min after the first ends — the continuity rule allows ≤ 25 min. Contradiction ⇒ no truck serves P1 twice ⇒ P1's 3 loads need 3 distinct trucks ⇒ K ≥ 3. | solver: ≤2 INFEASIBLE ✓
OBJ | Objective | minimise trucks used; tie-break: maximise the smallest margin over all rules | K*=3, min margin 25 ✓
VOL | Volume arithmetic | 24+16+8 = 48 m³; 48 ÷ 8 m³ = 6 loads | matches schedule rows ✓

## 3 Dispatch
Dispatch schedule — Thursday, Tikkurila plant, 3 trucks (T4/T5/T6 of the 6 booked)
Load | Pour | Element | Vol m³ | Truck | Batch T0 | Depart plant | Arrive site | Discharge start | Discharge end | Min from batch (end) | Gap to prev load (same pour) | Freshness margin (90−) | Window-open slack | Window-close margin | Turnaround buffer (this truck)
P1-L1 | P1 | Raft bay A | 8 | T6 | 06:05 | 06:15 | 06:40 | 07:00 | 07:10 | 65 | first load | 25 min | 0 min | 130 min | first trip
P1-L2 | P1 | Raft bay A | 8 | T4 | 06:35 | 06:45 | 07:10 | 07:10 | 07:20 | 45 | 0 min | 45 min | 10 min | 120 min | first trip
P1-L3 | P1 | Raft bay A | 8 | T5 | 06:25 | 06:35 | 07:00 | 07:20 | 07:30 | 65 | 0 min | 25 min | 20 min | 110 min | first trip
P2-L1 | P2 | Core wall | 8 | T6 | 08:00 | 08:10 | 08:45 | 08:45 | 08:55 | 55 | first load | 35 min | 75 min | 35 min | 25 min
P2-L2 | P2 | Core wall | 8 | T4 | 08:10 | 08:20 | 08:55 | 08:55 | 09:05 | 55 | 0 min | 35 min | 85 min | 25 min | 25 min
P3-L1 | P3 | Column heads | 8 | T5 | 08:20 | 08:30 | 08:50 | 09:15 | 09:25 | 65 | first load | 25 min | 45 min | 55 min | 25 min
TOTALS | — | 6 loads | 48 m³ | 3 trucks used (T4, T5, T6) | 3 trucks released (T1, T2, T3)
PLANT LOADING BAY (single-bay check)
Slot | Truck | Load | Bay occupied
06:05–06:15 | T6 | P1-L1 | exclusive
06:25–06:35 | T5 | P1-L3 | exclusive
06:35–06:45 | T4 | P1-L2 | exclusive
08:00–08:10 | T6 | P2-L1 | exclusive
08:10–08:20 | T4 | P2-L2 | exclusive
08:20–08:30 | T5 | P3-L1 | exclusive
TRUCK ITINERARIES
Truck | Trip 1 | Trip 2 | Note
T4 | P1-L2 batch 06:35 → discharge 07:10–07:20 → back ~07:45 | P2-L2 batch 08:10 → discharge 08:55–09:05 → back ~09:40 | 25-min turnaround buffer at plant
T5 | P1-L3 batch 06:25 → discharge 07:20–07:30 → back ~07:55 | P3-L1 batch 08:20 → discharge 09:15–09:25 → back ~09:45 | waits loaded 25 min for the PUMP (finishes P2-L2 09:05, relocates 10 min) — within 90-min rule
T6 | P1-L1 batch 06:05 → discharge 07:00–07:10 → back ~07:35 | P2-L1 batch 08:00 → discharge 08:45–08:55 → back ~09:30 | 25-min turnaround buffer at plant

## 4 Minimisation
Truck minimisation — why 3 is the minimum and what would change it
Step | Reasoning | Result
1. Volume floor | 48 m³ ÷ 8 m³ = 6 loads. With one-load-per-truck-trips, 6 loads need ≥ 2 trucks (a truck can reload). | ≥ 2
2. P1 gap proof (binding) | If one truck served two P1 loads: return 25 + load 10 + drive 25 forces the second discharge to start ≥ 60 min after the first ends — but the continuity rule allows ≤ 25 min. Contradiction ⇒ no truck serves P1 twice. | P1's 3 loads ⇒ ≥ 3 trucks
3. Solver proof | CP-SAT model with all rules: force ≤ 2 trucks → INFEASIBLE (proven, not timed out); force 3 → OPTIMAL with all margins ≥ 25 min. | K* = 3 (exact)
4. Independent checker | Separate rule-checker (not the solver) validates the 3-truck dispatch: PASS, zero violations. A hand-built 2-truck challenge plan was cross-examined — checker and model both rejected it (it used the 25-min drive for P2; true drive 35), confirming they agree. | PASS
5. Answer | Book 3 trucks (of the 6 booked): T4, T5, T6. Release T1, T2, T3 — action ACT-03. | 6 → 3
Binding constraint | The 25-min continuity rule on P1 (raft bay A): a truck's second P1 load would need a ≥ 60-min gap (return 25 + load 10 + drive 25) but only ≤ 25 min is allowed. Not the pump windows, not the 90-min rule, not plant capacity. | —
SENSITIVITY — trucks needed if reality differs
Variant | Change | Trucks needed
V0 | base (as given) | 3
V1 | discharge 15 min/load | 3
V2 | return leg +5 min | 3
V3 | all pump windows 15 min later | 3
V4 | gap relaxed to 30 min | 3
V5 | plant opens 06:30 | 3
V6 | discharge 15 + return +5 | 3
V7 | return leg +15 min (traffic) | 3
V8 | discharge 20 min/load | 3
V9 | P1 drive 15 min (hypothetical) | 2
V10 | P1 drive 20 min (hypothetical) | 2
MODEL AUDIT LOG — defects found and fixed during verification (transparency)
Defect | Effect | Fix
Truck-usage flag inverted (u=0 → 'some load on truck') | First solve reported 6 trucks — wrong | Literal corrected; result changed 6 → 3
Float objective maximised raw gap, not margin under the 25-min limit | Gaps pinned at exactly 25 min — zero compliance margin | Objective rewritten to maximise minimum margin
Different-truck pairs contributed 0 to the margin objective | Max-margin phase neutralised (min pinned at 0 by structural zeros) | Neutral value 200 for different-truck pairs
Hand-built 2-truck test plan used 25-min drive for P2 (true: 35) | False '2 trucks possible' challenge | Checker + pinned-model bisection both caught it; plan corrected

## 5 Checks
Checks & open items — verification log, escalation cards, action register — Rev 16 (2026-10-03)
Check | Detail | Status
Coverage: source items vs workbook | 17 source facts + 8 assumptions + 3 open items on sheet 1; all appear in the model (sheet 2) and schedule (sheet 3); no source item dropped (mapping verified by scan) | PASS
Volume consistency | Sheet 2 totals (48 m³, 6 loads) = sum of sheet 3 rows (6 × 8 m³) | PASS
Truck consistency | Distinct trucks on sheet 3 = {T4, T5, T6} = 3 = stated minimum | PASS
Rule checker (independent of solver) | All 6 loads: window, freshness, gap, turnaround, plant bay — zero violations | PASS
Lower bound | ≤2 trucks INFEASIBLE (solver) + hand proof (second P1 discharge ≥60 min after first ends vs ≤25 min allowed) | PASS
Empty cells | None — region-aware scan on the final saved file: 0 issues; non-applicable values stated explicitly ('first load', 'first trip') | PASS
Identifier provenance | Trucks T4/T5/T6 are from the booked list T1–T6 (user message); no fabricated IDs | PASS
O1 Return-leg drive time | Assumed equal to outbound (25/35/20). If Thursday AM traffic adds >20 min to a return leg, the 08:00/08:10/08:20 second batches shift later — truck count stays 3 (V7 tested +15 min) | ACCEPT / monitor
O2 Discharge rate | Assumed 10 min per load (≈48 m³/h). At 15–20 min/load the plan still holds with 3 trucks (V1, V8) | ACCEPT
O3 Plant single loading bay | Assumed. If the plant runs two bays, the plan is unchanged (it already satisfies single-bay) | ACCEPT
O4 Slump / retarder limits — TALLY ROW (authoritative statement = escalation card at row 22) | Not provided in the brief. Decision fields (options / consequence / recommend / decide-by) are held on the escalation card at row 22 — intentionally blank on this tally row so only ONE O4 statement carries them. | OPEN — confirm
O5 Pump priming / setup — TALLY ROW (authoritative statement = escalation card at row 23) | Not modelled. Verified: the P1 chain absorbs up to 25 min of priming delay (FAIL at 30). Decision fields (options / consequence / recommend / decide-by) are held on the escalation card at row 22 — they are intentionally blank on this tally row so only ONE O5 statement carries them. | OPEN — confirm
O6 P3 window-open wait | T5 arrives 08:50, discharges 09:15 (window opens 08:30) — 25 min on site, within the 90-min rule (batch 08:20 + 90 = 09:50 ≥ 09:25) | NOTED
O7 Robustness (verified by checker bisection) | Whole plan may shift +25 min (binds on P2 window close 09:30). Per-load batch slip with discharge slots fixed: P1-L1 +10, P3-L1 +25, others 0 — batches move as a chain, not independently. Freshness margins 25–45 min absorb discharge-start delays; P1 chain absorbs up to 25 min of pump priming. NOTE the two metrics: the 25-min figure is the tightest INTER-LOAD GAP / TURNAROUND margin; with discharge slots fixed the tolerable BATCH SLIP per load is 0 min on four loads, +10 (P1-L1), +25 (P3-L1) — from the checker bisection run, not from the margin figure. | VERIFIED
O8 Publish lessons after user review (crystallise wiki page) | Wiki lessons DRAFT filed (drafts/lessons-mixer-truck-minimisation.md) + history record hist_SQVaQ0su; publishing discharges this item | OPEN — process (discharged by ACT-06)
OPEN ITEMS — ESCALATION CARDS (options / consequence incl. cost of delay / recommendation / decide-by)
Item | Options | Consequence if unresolved (incl. cost of delay) | Recommendation | Decide by
O4 Slump / retarder limits not provided | (a) Confirm retarder dose & slump spec with Tikkurila for Thursday's mixes; (b) replan P3-L1 batch 08:45 — truck arrives 09:15 exactly when the pump is ready, zero wait | If retarder is limited, T5's 25-min wait loaded on P3-L1 (batch 08:20, discharge 09:15) risks the 90-min rule at ~09:50. Cost of late decision: past Wed 17:00 the 06:05 batching slot is at risk; the whole plan can only shift +25 min (binds on P2 window close 09:30), and P3-L1 falls back to the untested-in-advance 08:45 replan. | Recommend: (a) confirm dose today — it keeps concrete on site 25 min before the pump needs it (protects against pump-side delay). (b) if unconfirmed by Wed 17:00: freshness slack is actually LARGER under (b) — batch 08:45 + 90 = 10:15 limit vs placed 09:25 = 50 min slack, vs 25 min slack under (a) — but (b) has NO on-site buffer: any truck or plant delay lands directly on the pour. Trade-off stated; (a) preferred, (b) safe fallback. | Wed 17:00 (before Thu 06:00 batching) — DECIDER: PM (user), informed by Tikkurila plant
O5 Pump priming / setup not modelled | (a) Confirm priming time with pump operator; (b) none needed — verified: P1 chain absorbs up to 25 min of priming delay before the 90-min rule bites | If priming > 25 min, P1-L1/L3 breach freshness (verified at 30 min: FAIL). Cost of late decision: if discovered only on Thursday, the pour chain must be re-dispatched live. NOTE: the 25-min cap is STRUCTURAL — P1's batches are already at their latest feasible times (re-pinning them later fails the checker; the cap binds on freshness and T6's turnaround), so if the plant reports >25 min the dispatch is re-issued with a re-solve, not tweaked. | Recommend: accept risk up to 25 min; ACT-02 chases the operator's figure at Wed toolbox; if >25 min, re-solve and re-issue before Wed 17:00 | Wed 17:00 (figure from site engineer at Wed toolbox) — DECIDER: PM (user)
O6 Washout / stand-by between pours | No action — verified no effect on truck count or schedule | None (turnaround buffers 25 min exceed typical washout). Cost of late decision: none (verified no effect). | Recommend: note in dispatch; no decision needed | —
NOTE: no prior action register exists (single-source chat brief; this is the project's first register) — no carry-over rows to walk done/moved/dropped.
Ref | Action | Owner | Due | Source
ACT-01 | Confirm slump/retarder limits with Tikkurila for Thursday's mixes (or trigger fallback: P3-L1 batch 08:45) | PM (user) + Tikkurila plant | Wed 17:00 (clock deadline) | Open item O4; spec not provided in brief
ACT-02 | Confirm pump priming/setup time with pump operator | Site engineer | Wed toolbox (before Thu 06:00) | Open item O5
ACT-03 | Release trucks T1, T2, T3 from Thursday's booking (keep T4/T5/T6) | PM (user) authorises; plant desk executes | Wed 17:00 (clock deadline — batching starts Thu 06:00) | Solver result: 3 trucks proven minimal
ACT-04 | Issue dispatch sheet to plant desk & pump operator (batch times 06:05/06:25/06:35/08:00/08:10/08:20) | PM (user) | Wed 17:00 | Spec 90-min batching-to-placement rule + 25-min continuity rule (operative basis of the notice); schedule detail: Sheet 3 Dispatch
ACT-05 | Lessons: wiki DRAFT filed (pending user approval) + history record hist_XAJMGq4z (superseded by hist_SQVaQ0su) added | PM Assistant (this chat) | Draft done today; publish after user review | Model audit log, sheet 4
ACT-06 | Publish the wiki lessons draft after user approval (crystallise) | PM Assistant (this chat) | On user approval of drafts/lessons-mixer-truck-minimisation.md (open item O8) | Model audit log, sheet 4
ACT-07 | EMAIL FALLBACK: if Public links are not enabled by Wed 17:00, send the final .xlsx (this rev) directly by email to plant desk + pump operator | PM (user) | Trigger: Wed 17:00 if links still local-only | Deliverables block, this sheet
O8 Publish lessons draft after user review (crystallise wiki page) | (a) crystallise after user approval; (b) user declines — discard draft | Cost of late decision: none (lessons already drafted; history record hist_SQVaQ0su added) | Recommend: (a) crystallise after user approval | Owner: PM Assistant — due after user review
LESSONS FILED
Lesson | Filed to
Reify solver flags by exact clause form (one inverted literal made 6 trucks look optimal); audit the objective's intent, not just constraints (raw gap vs margin-under-limit; structural zeros pinning a max-min objective); cross-examine solver results with an independent checker and hand-built challenge plans (it caught a wrong drive-time input) | Org wiki DRAFT (pending approval) + history DB hist_XAJMGq4z (superseded by hist_SQVaQ0su) — see ACT-05/O8
ACT-04 DRAFT NOTICE — BODY (content block, not an action row: owner/due/source live in the ACT-04 register row above; operative basis quoted in the Basis line: the spec's 90-min batching-to-placement rule and the 25-min continuity rule)
To: | Tikkurila plant desk; pump operator (cc site engineer)
Subject: | THURSDAY POUR DISPATCH — 3 trucks (T4/T5/T6), batch times as below — please confirm by Wed 17:00
Body 1: | For Thursday's three pours (P1 raft bay A 24 m³, P2 core wall 16 m³, P3 column heads 8 m³ — 48 m³, six 8 m³ loads), we will run THREE mixer trucks, not six: T4, T5, T6. Please release T1, T2, T3 from tomorrow's booking.
Body 2: | Batch (loading-start) times at Tikkurila: 06:05 (T6, P1-L1), 06:25 (T5, P1-L3), 06:35 (T4, P1-L2), 08:00 (T6, P2-L1), 08:10 (T4, P2-L2), 08:20 (T5, P3-L1). Each truck runs two loads; 25-min turnaround buffers are built in.
Body 3: | Discharge plan at site: P1 07:00 / 07:10 / 07:20; P2 08:45 / 08:55; P3 09:15. The pump finishes P2 at 09:05 and relocates 10 min — P3 discharge starts 09:15 sharp.
Body 4: | Please confirm two things by Wed 17:00: (1) the 3-truck booking and the batch times above; (2) slump/retarder limits for the mixes, given T5 waits loaded 25 min on the P3 load (placed within 90 min of batching — batch 08:20, discharge 09:15).
Basis: | Spec rule: concrete must be PLACED WITHIN 90 MINUTES OF BATCHING (governs the P3-L1 loaded wait). Dispatch rule: MAX 25 MINUTES BETWEEN LOADS ON THE SAME POUR (sets 3 trucks — a truck's second P1 load would start ≥60 min after the first ends). Detail: audit workbook Thursday_pour_dispatch_audit.xlsx, sheets 3–4.
DELIVERABLES IN THIS PACK
Deliverable | Location / status
Audit workbook (this file) | Thursday_pour_dispatch_audit.xlsx — 5 sheets. Share link: CREATED at Rev 14 content (snapshot, 7 days) — URL issued in chat and visible in Settings → Shared links; NOT printed in this file (printing it would stale the snapshot on the next edit). CREATED, NOT YET CLIENT-ACCESSIBLE (local install, tunnel OFF). Owner for enabling Public links: PM (user) → platform admin, by Wed 17:00 (Private Sync → Database app → Configuration). Fallback: ACT-07 (email the .xlsx).
Interactive dispatch artifact | Artifacts/thursday-dispatch-3-trucks-tikkurila.html — PUBLISHED (author Rev 9; file unchanged since). Share link: CREATED at Rev 14 round (snapshot, 7 days) — URL in chat / Shared links manager, not printed in-file (same snapshot-stability rule). CREATED, NOT YET CLIENT-ACCESSIBLE (same platform note, owner and date as the workbook).
Wiki lessons draft | drafts/lessons-mixer-truck-minimisation.md — pending user approval (open item O8)
History DB records | hist_SQVaQ0su (rev 2, supersedes hist_XAJMGq4z (superseded by hist_SQVaQ0su) — supersession recorded as a field in the record)
REVISION LOG — scheme: Rev N = AUTHOR revision of this pack; the REVIEW ROUND each rev answers is named inside the entry
Rev | What entered
Rev 1 | Initial 5-sheet build from the verified 3-truck solve
Rev 2 | Lower-bound corrected to the 60-min forced-gap chain (95-min figure withdrawn everywhere)
Rev 3 | Escalation cards (options/consequence/recommend/decide-by) + action register added
Rev 4 | P3-L1 wait corrected: waits for the PUMP (AS-09 shared pump, 10-min relocation); cross-pour transitions verified
Rev 5 | O4 option arithmetic corrected: (b) freshness slack 50 min vs 25 min under (a); trade-off = on-site buffer vs freshness
Rev 6 | Identifiers unified: assumptions AS-01..AS-09, actions ACT-01..ACT-05 (no collisions; zero stale refs)
Rev 7 | ACT-04 draft notice text added to the pack (marked DRAFT, not issued)
Rev 8 | O5 structural cap verified and stated: >25 min priming ⇒ re-solve and re-issue (batch re-pin and T6-shift both fail the checker)
Rev 9 | Interactive artifact published (timeline, itineraries, proof, sensitivity)
Rev 10 | DELIVERABLES block added; artifact status stated in the pack
Rev 11 | Share links created (snapshot, 7 days); numbering unified to this log; O-series provenance stated
Rev 12 | Rev 12 (author) — fixes from REVIEW ROUND 14: ACT-04 notice header relabeled; deciders named on O4/O5; prior-register note; share-link status corrected
Rev 13 | Rev 13 (author) — REVIEW ROUND 16: metadata-only link update; tally reconciled; scope note; ACT-04 source corrected
Rev 14 (author) — REVIEW ROUND 17 | ACT-06/ACT-07 added (orphan promises closed); revision scheme disambiguated (author rev vs review round); share-link URLs removed from in-file text (snapshot-stability rule)
Rev 15 (author) — REVIEW ROUND 18 | ACT-06 (publish lessons after user approval) and ACT-07 (email fallback) added to the register; register 6 -> 7 rows; both share links created at that content
Rev 16 (author) — REVIEW ROUND 20 | O5 rendered as ONE authoritative statement (tally row is now an explicit pointer to the card; decision fields held only on the card); O8 given its own tally row with status + evidence pointing at ACT-06; Rev 14 log row repaired